# Clean Frontline: Improving hospital surface hygiene in Cambodia

Presented by Giorgia Gon, LSHTM, on 18 September 2025

Host: UNC Healthcare Facilities Community of Practice

## TL;DR

A pragmatic, low-cost TeachClean / WHO–adapted training + supportive supervision package was rolled out as a stepped‑wedge trial across 13 referral hospitals in Cambodia. Monthly microbiological sampling from May 2022–Mar 2023 showed a measurable improvement in surface cleanliness. Surface-level metrics improved substantially in some analyses (~30–40% better), while the hospital‑level average effect was modest (~5% increase). The package is affordable at approximately USD 5,000 per hospital and effectively equips and empowers cleaners. However, it faces consistent barriers: too few staff hours, inadequate supervision, weak leadership prioritization, and shortages of basic supplies, including cloths, buckets, and hand hygiene bottles.

## What was done (short method snapshot)

- Design: Stepped‑wedge cluster randomized trial — all 13 hospitals received the intervention; the timing of rollout was randomized. Thirty surface swab samples per hospital per month; two months baseline with continuous monthly sampling May 2022–March 2023.

- Intervention: TeachClean (adapted by WHO) training-of-trainers model — 52 local Cleaning Champions trained; champions trained peers at facility level; ~271 people trained at facilities (51 of them dedicated cleaners in the targeted wards). The package emphasizes visual aids, demonstrations, adult learning and realistic schedules.

- Microbiology & outcome: Dip-slide sampling with pathogen-specific side (Staphylococcus aureus was assayed). “Clean” was defined as under ~2.5 colony‑forming units/cm².

- Sample size: ~3,900 samples collected; 3,822 included in final analysis.

## Key results (what actually changed)

- Effect: Study team reported a statistically positive effect overall. Surface‑level analyses suggested a ~30–40% improvement in microbiological cleanliness after training in some metrics, while aggregated hospital‑level averages showed a modest ≈5% improvement pre vs post (these figures reflect different ways of aggregating the same data — surface‑sample vs hospital average).

- Cost: Implementation costs were low — roughly USD 5,000 per hospital for training and minimal supplies.

- Qualitative: Cleaners reported improved knowledge, confidence, and role recognition. Sustaining change was difficult due to practical constraints: staff shortages, limited paid hours, high staff turnover, poor leadership/managerial prioritization, and shortages of basic supplies like cloths.

## What mattered most (practical takeaways)

- Training works. The package is effective, inexpensive and scalable as an entry point. It substantially improves cleaner knowledge, technique and some surface‑level microbiology.

- Local adaptation & realism are critical. Realistic cleaning schedules (given actual staff hours), simple visual aids and low‑literacy teaching methods made the difference.

- Supplies > sophistication. Access to essential, cheap supplies (cloths, buckets, basic PPE, personal hand‑rub bottles) is often the main bottleneck. Prioritizing access to those supplies is more important than pursuing complex technology.

- Supervision & leadership make or break sustainability. The impacts of training fade without continued supportive supervision and explicit managerial prioritization and budgeting.

- Measurement is time-intensive but necessary. Results from microbiological sampling are variable and seasonal — you need large sample sizes and time‑trend data to detect effects.

## Recommendations — for ministries, hospital managers, funders, implementers

- Integrate TeachClean content into national IPC guidance and formal training curricula — Cambodia is already moving in this direction.

- Budget for ongoing supportive supervision (not just a one‑off training). Supervisors are the multiplier.

- Fund the basics: provide sufficient reusable cloths (or affordable disposable options), buckets, simple PPE and hand‑rub bottles to cleaners as part of routine budgets.

- Set realistic cleaning schedules with facility staff — prioritize patient‑zone, high‑touch surfaces when staffing is limited.

- Plan for measurement & learning: use monthly microbiological sampling during rollout to monitor, but expect variability — complement with process indicators (fluorescent gel checks, observations, knowledge tests).

- Do a costed scale‑up analysis before national rollout so ministries understand recurrent costs (supervision, supplies, replacement cloths).

## Practical tools & resources

- Clean Frontline trial registration & materials: https://clinicaltrials.gov/study/NCT05540886?locStr=Cambodia&country=Cambodia&page=2&rank=17

- WaterAid policy/learning brief (Clean Frontline summary & recommendations): https://washmatters.wateraid.org/publications/breaking-infection-chain-supporting-essential-work-cleaners-cambodia-healthcare-facilities

- WHO environmental cleaning training package (TEACH CLEAN / WHO adaptation): https://iris.who.int/handle/10665/379551

## Caveats & unanswered questions

- The trial measured microbiological cleanliness (a plausible intermediate outcome), not healthcare‑associated infections (HAIs); detecting HAIs reliably requires blood culture systems and better clinical surveillance than most participating hospitals currently have.

- Results varied substantially from month to month and by hospital —  plan for sufficient sample sizes and time to see trends.

Credits & contacts: Presented by Giorgia Gon (LSHTM) on behalf of the Clean Frontline team; hosted by UNC (emcee Ryan Cronk; Zoom coordination by Darcy Anderson and Liam Powell).